## Sheet1
ID Number | Level | Category | Description | Work time | Due date | Lead | Completed | Comments and Next Steps
1 | Goal | Land Protection | Aggressively Accelerate Land Protection for Harmony Grove Canyon
1.1. | Objective | Land Protection | Protect 80% of the land in Harmony Grove Canyon by 2009 | 6/04 - 12/09 | 2009-12-01
1.1.1 | Task | Land Protection | Create a Conservation Plan for Harmony Grove Canyon - map, parcel inventory, acquisition targets. | 7/04-9/04 | 2004-09-01 | Wittwer
1.1.2 | Task | Land Protection | Begin Land Owner Contact Program to meet key landowners. | 9/04-12/04 | 2004-09-01 | Wittwer
1.1.3 | Task | Land Protection | Expand and formalize Land Owner Contact Program. | 3/05-12/09 | 2005-03-01 | New ED
1.1.4 | Task | Land Protection | Work to acquire Resnick 100 by September 2005. | 7/05 - 9/05 | 2005-09-01 | Wittwer, New ED
1.1.4a | Task | Land Protection | Create team to work on Resnick Property. | 2004-07-05 | 2004-07-04 | Wittwer | Done | Wittmer, Barker and Delano to work on this
1.1.4b | Task | Land Protection | Draft letter to Resnick. | 7/04-8/04 | 2004-08-04 | Delano
1.1.5 | Task | Land Protection | Work to follow and influence proposed New Urban West development. | 7/04-9/05? | 2004-09-05 | Rady
1.1.5a | Task | Land Protection | Build team and investigate status, report to board. | 7/04-9/04 | 2004-09-04 | Rady
1.1.5b | Task | Land Protection | Continue to follow New Urban West development proposal, qtly reports to board or as needed | 9/04-9/05 | 2004-09-05 | Rady
1.1.6a | Task | Land Protection | Create a compelling presentation : "Conservation Vision for Harmony Grove Canyon" | 7/04 - 8/04 | 2004-08-01 | Barker |  | Build presentation from Wittmer's draft of Conservation Plan for Harmony Grove, expand presentation into a Creek-wide Vision for Escondido Creek.
1.1.6b | Task | Land Protection | Make 4 presentations to neighbors of Conservation Vision for Harmony Grove | 9/04 - 12/04 | 2004-12-04 | Barker |  | Need to determine how this relates to larger Vision for the Creek presentations.
1.1.7 | Task | Land Protection | Investigate local sewer and outfall capacity and other infrastructure constraints on development. Report back to board with recommended actions. | 7/04 - 11/04 | 2004-11-01 | Harmon
1.1.8 | Task | Land Protection | Explore scenic byway designation as protection tool for Harmony Grove Road | 7/04 -12/04 | 2004-12-01 | LeLevier |  | Constanzo and Barker to get report, LeLevier to carry out research and report to board.
2 | Goal | Institutional Capacity | Build TECC’s Institutional Capacity
2.1 | Objective | Institutional Capacity | Hire an Executive Director | 7/04 -1/05 | 2004-01-05 | Rady |  | Staffing Committee
2.1.1 | Task | Institutional Capacity | Create a Staffing Committee of the Board to oversee staff and institutional issues. | 2004-07-04 | 2004-07-04 | Rady | Done
2.1.1a | Task | Institutional Capacity | Draft and circulate Job Description for Executive Director position, interview candidates. | 7/04 -12/04 | 2004-12-04 | Rady
2.1.2 | Task | Institutional Capacity | Institute a Transition Plan to move TECC toward hiring a full-time executive director | 7/04 -12/04 | 2004-12-01 | Wittwer
2.1.2a | Task | Institutional Capacity | Draft written Transition Plan with six month objectives, goals and deliverables | 2004-07-04 | 2004-07-04 | Wittwer
2.1.2b | Task | Institutional Capacity | Review Deb LeLevier's current performance, discuss new roles, responsibilities, goals and objectives during transition phase and when new ED comes on board. | 2004-07-04 | 2004-07-04 | StaffingCom | Done
2.1.3 | Task | Institutional Capacity | Move staff from contractor status to employee status | 7/04 -10/04 | 2004-10-04 | Wittwer, StaffingCom
2.2 | Objective | Institutional Capacity | Raise $250,000 in cash or pledges to cover costs of expanded operations | 7/04 -12/04 | 2004-12-04 | Costanzo |  | See 6.1 below.
3 | Goal | Board Development | Strengthen the board and its capacity
3.1 | Objective | Board Development | Recruit and engage 4-5 new board members | 7/04 - 12/04 | 2004-12-04 | Nom.Com.
3.1.1 | Task | Board Development | Establish an Executive Committee and Nominating Committee | 2004-07-04 | 2004-07-04 | Rady |  | Nominating Committee: Delano and Harmon
3.1.2 | Task | Board Development | Develop board matrix, identify at least 24 candidates with board input | 7/04 - 9/04 | 2004-09-04 | Nom.Com. |  | Nominating Committee: Delano and Harmon
3.1.3 | Task | Board Development | Meet and recruit 4-5 new board members | 9/04 - 12/04 | 2004-12-04 | Nom.Com. |  | Nominating Committee: Delano and Harmon
3.1.4 | Task | Board Development | Establish program to orient and involve new board members | 12/04 - 7/05 | 2004-07-05 | Nom.Com. |  | Nominating Committee: Delano and Harmon
3.1.5 | Task | Board Development | Create board orientation packet | 2004-12-04 | 2004-12-04 | Nom.Com. |  | Nominating Committee: Delano and Harmon
3.1.6 | Task | Board Development | Meet new board members and secure '"goals and action commitment" w/in first 6 months. | 1/05 - 7/05 | 2004-07-05 | Nom.Com. |  | Nominating Committee: Delano and Harmon
3.1.7 | Task | Board Development | Establish board term limits (three year terms, max three conseq. terms). | 2004-01-05 | 2004-01-05 | Nom.Com. |  | Nominating Committee: Delano and Harmon
4 | Goal | Community Support | Build and Market a “Vision for Escondido Creek”
4.1 | Objective | Community Support | Create, in partnership with others, "The Vision for Escondido Creek" | 7/04 - 10/04 | 2004-10-01 | Barker |  | Steve Barker will establish team to do this
4.1.1 | Task | Community Support | Create rough working draft, working framework, and working presentation for the Vision by August. | 7/04 - 8/04 | 2004-08-01 | Barker/Wittwer
4.1.2 | Task | Community Support | Use Conservation Plan and Vision for Harmony Grove Canyon as key building block. | 7/04 - 10/04 | 2004-10-01 | Barker/Wittwer
4.1.3 | Task | Community Support | Consult with San Elijo Lagoon Conservancy to get input and add their plans for the lagoon into the overall Vision statement. | 7/04 - 10/04 | 2004-10-04 | Barker/Wittwer
4.1.4 | Task | Community Support | Meet with other leading groups to secure preliminary input and add their plans. | 7/04 - 10/04 | 2004-10-04 | Barker/Wittwer |  | Continue to contact and meet with groups as part of the outreach and as needed to refine the Vision and gain additional support.
4.1.5 | Task | Community Support | Add a proposed well-defined trail system for the Creek as a map and chapter to the vision. | 7/04 - 10/04 | 2004-10-01 | Olmstead |  | See also "Supporting Issues" section in text.
4.1.6 | Task | Community Support | Add a goal and set of objectives to eliminate the concrete channel and restore the Escondido section of the creek. | 10/04 - 12/04 | 2004-12-04 | Barker
4.1.7 | Task | Community Support | Add a section that addresses the goals and objectives for the upper reaches of the Creek into the vision. Identify partners working in the area. | 10/04 - 12/04 | 2004-12-01 | Delano/Harmon
4.1.8 | Task | Community Support | Add goals that would return the Creek into a "living stream". | 10/04 - 12/04 | 2004-12-01 | Delano/Harmon
4.1.9 | Task | Community Support | Produce revised and refined document: "The Vision for Escondido Creek". | 2004-12-04 | 2004-12-04 | Barker
4.2 | Objective | Community Support | Market the Vision for Escondido Creek to the Community | 8/04 - 9/05 | 2004-09-05 | Barker/New ED
4.2.1 | Task | Community Support | Design and implement a series of one-hour "field trip introductions" to Harmony Grove for small groups (10-12). | 7/04 - 12/04 | 2004-12-01 | Wittwer
4.2.1a | Task | Community Support | Assign specific board members to conduct each field trip. Conduct 4-6 trips for 10-12 people each by December. | 7/04 - 12/04 | 2004-12-04 | Wittwer |  | With board assistance
4.2.1b. | Task | Community Support | Design and carry out a specific structured follow-up by each board member of every person attending field trip. | 7/04 - 12/04 | 2004-12-01 | Wittwer |  | With board assistance
4.2.2 | Task | Community Support | Design and implement a series of community presentations/workshops that present The Vision for the Creek to targeted community groups. Secure their feedback and buy-in for the vision. Hold at least one presentation per month through December 2004. | 7/04 - 12/04 | 2004-12-01 | Wittwer |  | With board assistance
4.2.3 | Task | Community Support | Develop a compelling and revised presentation and materials for The Vision for the Creek. | 12/04 - 3/05 | 2005-03-05 | Barker/New ED
4.2.4 | Task | Community Support | Design an aggressive community outreach campaign to bring The Vision for Escondido Creek to a wide range of targeted groups and audiences in 2005. | 1/05 - 12/05 | 2005-12-01 | New Exec. Dir.
4.3 | Goal | Community - Supporting Issue | Strengthen the Escondido Creek Watershed Alliance (ECWA) and Explore potential for a Joint Powers Authority | 7/04 - 12/04 | 2005-12-01 | Harmon
4.3.1 | Task | Community - Supporting Issue | Investigate the pros and cons of a Joint Powers Authority like the San Dieguito's watershed, and report to the board prior to January 2005. | 10/04 - 12/04 | 2005-01-01 | Harmon
4.3.2 | Task | Community - Supporting Issue | Present a well-supported "Vision for Escondido Creek" to the ECWA in 1/05 to secure its support. | 2004-01-05 | 2004-01-05 | Harmon
5.1 | Task | Supporting Issues | Review TECC’s existing membership program – recruitment, benefits, newsletter, annual appeal and renewal efforts – and make recommendations to the board for appropriate improvement. | 1/05 - 7/05 | 2004-07-05 | New Exec. Dir.
5.2 | Task | Supporting Issues | Review TECC's financial controls and procedures, along with an investigation into how it might achieve a formal audit at an affordable price. | 7/04 - 12/04 | 2004-12-01 | Wittwer/Barker
5.2 | Task | Supporting Issues | Review the "parking lot" issues not fully addressed during the strategic planning session on a qrtly. Basis to ensure appropriate follow-up. | 10/04, 2/05 | 10/04 & 2/05 | Rady
6 | Goal | Fundraising | Raise the funds needed to expand operations and TECC's capacity, protect and care for Harmony Grove Canyon, and build broad support to achieve "The Vision for Escondido Creek"
6.1 | Objective | Fundraising | Raise $250,000 by December to meet costs of expansion. | 7/04 - 12/04 | 2004-12-01 | Costanzo |  | see Objective 2.2 above.
6.1.1 | Task | Fundraising | Ensure 100% board participation -- every board member gives. | 7/04 - 12/04 | 2004-12-01 | Costanzo
6.1.2 | Task | Fundraising | Ensure 100% board participation -- every board member also "gets". | 7/04 - 12/04 | 2004-12-01 | Costanzo
6.1.3 | Task | Fundraising | Develop fundraising campaign materials: "Harmony Grove Canyon Campaign" | 7/04 - 9/04 | 2004-09-01 | Costanzo
6.1.4 | Task | Fundraising | Develop preliminary calculation of private dollars needed to catalyze Harmony Grove Conservation Plan -- add to fundraising goal as appropriate. | 7/04 - 9/04 | 2004-09-01 | Wittwer/Costanzo
| Note | Fundraising | see other related tasks above regarding field trips, community presentations, membership, new board member recruitment.